## Process plan
6-week consultation timeline: Milestones and detailed tasks | January | [17 empty] | February | [27 empty] | March
| 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 22 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Heather to meet with teachers to gather full list of question and challenges
2.Consultation letters sent out to all staff, parents and interested parties
3.Information meeting for staff with David Waugh - questions prepared prior to meeting
4.Information evening for parents with David Waugh, Governors, SLT and TTLP personnel
5.Consultation period ends
6. Full GB Spring meeting to discuss outcomes of Consultation and next steps
Action key
Milestones
Action for person 1 (name TBC)
Action for person 2 (name TBC)
Action for person 3 (name TBC)
Action for person 4 (name TBC)
Action for person 5 (name TBC)

## Key Outcomes
| Outcome 1 | Outcome 2 | Outcome 3 | Outcome 4 | Outcome 5
| All children who attend Disley Primary School will have access to high quality teaching, resources and extended curriculum opportunities to allow them to achieve and attain well above National levels | Staff at Disley Primary School will be well supported, both within their own school and also within the MAT. This will include high quality professional development opportunities and peer-to-peer support. | Disley Primary School is able to sustain high quality staff and buildings financially in the long-term. | All children who live in Disley are able to attend Disley Primary School. | Disley Primary School is able to retain its' uniqeness as a school serving its' own community with the particular needs that brings.
Note: When you type the Outcomes into the above cells they will autopopulate onto the appropriate cells within the 'Questions&challenges' and 'Performance management' tabs
Key

## Questions&challenges
| Outcome 1 |  |  | Outcome 2 |  |  | Outcome 3 |  |  | Outcome 4 |  |  | Outcome 5
| All children who attend Disley Primary School will have access to high quality teaching, resources and extended curriculum opportunities to allow them to achieve and attain well above National levels |  |  | Staff at Disley Primary School will be well supported, both within their own school and also within the MAT. This will include high quality professional development opportunities and peer-to-peer support. |  |  | Disley Primary School is able to sustain high quality staff and buildings financially in the long-term. |  |  | All children who live in Disley are able to attend Disley Primary School. |  |  | Disley Primary School is able to retain its' uniqeness as a school serving its' own community with the particular needs that brings.
| Questions / challenges | Answer / outcome | Appropriately answered / resolved? | Questions / challenges | Answer / outcome | Appropriately answered / resolved? | Questions / challenges | Answer / outcome | Appropriately answered / resolved? | Questions / challenges | Answer / outcome | Appropriately answered / resolved? | Questions / challenges | Answer / outcome | Appropriately answered / resolved?
Parents | What are the benefits of moving from being a mainstream school to an academy school? | Joint administration facilities, Joint school accountability processes, Joint commissioning of support services, e.g. Counsellor, CAMHs, Early Intervention Worker, Learner Mentors, Learner Tutors, Health Worker. Staff CPD opportunitues - funding is available for Leadership training, joint staff training, opportunities for peer-to-peer support The children would indirectly benefit from all of the above. | Yes | I understand the need to join a trust in the current funding climate. Why this Trust and not another Trust? | The priciples of TTLP MAT are based around the needs of the community and supporting each school to be its' best. It is a well-established community now and would mean that Disley's individual needs would be known and supported. . |  | Given the Council’s commitment to further housebuilding within Disley, the school will presumably have to continue to expand to create capacity, which will require substantial investment from local and/or national government. Will the conversion to an academy put us in a better or worse position regarding this extra funding and the school’s ability to lobby for it? | Funding for capital building as a Maintained LA school comes via the LA. The LA is a shrinking authority and there are less opportunities to bid for funding for any capital build. As a MAT the academy would have access to a different funding pot, direct from the Education and Skills Funding Agency (EFSA) and the Condition Improvement Fund (CIF). In the long-term we would not be any worse off than we are are now as a Maintained school. Any future school building would need ot be funded by either the LA or central government. |  | Increased capacity- Could this be explained at the meeting – wondering if this means if Disley is over capacity on intake one year and Lostock under would child go to Lostock? | No, Parental choice still is a priority; if a parent applies for a place at Disley then, as long as the Admission Code (National) is followed, a place would be offered at Disley. As an academy we would have more freedom over our admission number, meaning that we could decide whether to change the PAN (Published Admission NUmber). We would follow the Code and have to go through a consulattaion period, as we did before. No child would be made to attend another school in the MAT unless it was out of choice. |  | What discretion does each school individually have in the academy to ensure it is fully still able to listen to the voices of the children and parents to meet the needs of the children? | Most functions currenty carried out by the Governing Board will continue to be carried out by them, These include aspects of school unique to our school and community e.g appointing staff, deciding on uniform, raising funds for the local community, running after school clubs etc. The joint policies shared by all schools in the MAT will be around Pay, HR contracts, pensions, complaints. We currently adopt Cheshire East model policies for these areas so the Trust replaces the function of the Local Authority.
| What disruption are the children likely to experience through the change? | Very little disruption is envisaged. Colleagues in other schools who have gone through this process support this. | Yes | Will the teachers go to teach at other schools? | No, unless they choose to or by joint agreement for a time. Staff would teach in the school that employed them. |  | How much is the school paying each year for the privilege of being part of the MAT? | 4% of the budget received directly from the Government would be paid back into the MAT for central services. Currently the school has X% retained by the LA for central services. |  |  |  |  | How would it work with the academy and the current governing body? | Each school would have its' own local Governing Board, with a Chair. The Trust delegates responsibility to te local GB to carry out the day-to-day running of the school, including employing staff, deciding on a curriculum, monitoring standards, managing a budget . The Trust would oversee the core functions of finance and teaching standards.
| What are the values and principles of the new academy? How would these play out in the teaching and learning? | Support, Protect, Advise, Challenge and Empower. Each school would be autonomous but have the support of the MAT |  | What is known about the future intentions of TTLP? How many schools is it likely to incorportae? | See p/pt persenatation on GH and school website. The MAT will be based around 2 communites initally - around 6 schools. There is no long-term intention to grow too big. For maximum finacial benefits the MAT needs to have 6,000 + pupils. |  | What benefit is the school going to receive to justify the expenditure? | The potentail benefits would be around joint purchasing, a shared vision for the community of schools, access to good quality CPD for staff. See the p/pt presenttaion on school website and GH |  |  |  |  | Will the school still be able to maintain its own character and not be absorbed into the larger corporate model? | Yes. The articles of association state that each individual school is governed by a local Governing Board and has control of its' own budget, internal policies, staff appointments. Although the MAT is based around a Community of schools, the school's own individual characteristics will still be recognised and allowed to stand.
| Would children with additional needs be potentially expected to travel to different schools to access different classes/ resources – Logistics and cost of this travel would be a question | No, children would be educated and supported at their own school as is the case now. | Yes | To what extent would the Trust be underwritten by the Local Authority? What is the contingency plan should the Trust get into finacial difficulties? | As with a Maintained school, the Trust requires each school to draw up a 3-year budget plan, which is scrutinsed by the Trust Board and CFO. Any foreseen defciit would require action taking, just as it is now as a Maintained school. The LA would not underwrite any budget deficit. The Trust is audited annually. Forward planning of budgets would ensure that the Trust did not fail financially. |  | TTLP has not been trading for very long. What due diligence is being undertaken with regards to their trading position and financial viability? and what will be made available to parents? | The Headteacher and Governors are carrying out a thorough due diligence on aspects such as the finance of the MAT, delegation, articles of assocation, Details of this cannot be made available to parents due to the confidentiality of some of the information. |  |  |  |  | Will the local governing body have real leadership and governance? | Yes, the scheme of delegation sets out what authority the local Governing Board has. It has the power to decide on its' budget and spending priorities, to make staff appointments and many other decisions as it does now as a Maintained School under Cheshire East.
| What assurances can be provided about the curriculum that would be followed under an academy? | As now, each school would be able to choose and set its' own curriculum. We are in the process of reviewing our curriculum now as a maintained school and this would not change if we moved to an academy. | Yes |  |  |  | Staff will presumably transfer under TUPE to the Trust and their rights will initially be protected but only at the point of transfer? What protections will be provided post transfer to prevent the Trust making significant variations to terms for Economic, Technical and Organisational reasons? | The MAT is using the Burgundy Book for Teachers Pay and Conditions and the Green Book for Support staff as part of it's articles. This means that the same terms and conditions for staff will exist after the initial TUPE process has taken place. |  |  |  |  | Will the strong traditions and ethos of Disley Primary be in danger of being ignored? | No, see the responses above. The Governing Board is undertaking thorough due diligence to ensure that this MAT would not jeapordise DPS traditions. As TTLP model is based around SPACE (Support, Protect, Advise, Challenge and Empower) then the autonomy of the school is safe.
| What impact would joiing a MAT have on Pupil Premium funding? Is there a risk that funds intended for DPS pupils could be retained by the Trust? | No, each school retains its' own PPG funding for use with the pupils that are at that schools. School is accountable to Ofsted and Governosr for the impact of funding spent on PP pupils. | Yes |  |  |  | Will it be that the same money is allocated for repairs for each school as it is now but we just get a better rate for the work? | Each school will still have its' own budget for building replairs, managed by the local Governong Board. Large projects may occur and schools can agree to pool money to ensure a better shared resource. |  |  |  |  | Why now? Is this all about the education funding lanscape? | The place of Local Authorities in education is being reduced As more schoolare choosing to convert to a MAT, this leaves fewer resources available for the LA to support schools. We are seeing the impact of this now with Cheshire East in the amount of support we receive in areas such as Finance, SENd and staff training.
| How would DPS be governed and qualities checked? Would decisions made by Heather Taylor be overridden by the CEO/Head of PHS? | The local Governing Board would make most decsions for the school, as it does now. Schools within the MAT would be accounatble to each other. Standards in each school would be scrutnised by all schools. The CEO would not override a decision made by the Disley Head. |  |  |  |  | How would our budget as an academy compare to being a Maintained school? | It is difficult to draw up a 3 year budget without knowing the exact details of the funding at source. However, the top-slice taken by the MAT would be 4% and we currently pay around 9% to Cheshire East There would also be savings to made on contracts such as insurance and photo copiers, as evidenced by Lostock Hall's budget now compared to being a Maintained school. |  |  |  |  | Would funds raised by Disley's PTA be used by other schools if money is pooled? | No, each school in the MAT would retain any funds raised through its' own PTA or other donations.
| Is there a risk that if the school cannot work financially that it coul dbe closed and merged with one of the other academy schools? | The risk is no great with an academy than it is with a Maintained school, A Maintained school has to have a 3 year budget approved by the LA and monitored termly. If a LA school was in severe finacial difficulties, despite this regular monitoring and actions being implemented, the LA would intervene, remove the Governing Board and replace them with a strategic board who would act to rectify the problems. This could result in staff being dismissed, or the school being closed. As an academy the Trust would replace what the LA would be doing.
Staff |  |  |  | Will staff have to work across different schools within the MAT? | As above - no, unless they choose to. |  | Will staff's pay date change and will there be new contracts and pay and conditions? | [5 empty] | Could we be sharing a Headteacher in the future? | No. Each school would have its' own Headteacher. There would be a position for an Executive Head in each MAT Community who would have oversight of the schools attainment and teaching and learning, and act as support for the Headteachers.
|  |  |  | Will there be opportuinities for professional development? | Staff CPD opportunitues - funding is available for Leadership training, joint staff training, opportunities for peer-to -peer support |  | How are maternity rates different? (moving from LA as employer) | [5 empty] | If other schools in the MAT have a lower Ofsted grade than ours, will this mean extra inspections or affect us in any way? | Each school would be inspected separately. A lower Ofsted grade by one school would only impact on the other schools in the MAT in that they would be expected to offer support to that school. It is similar to what we are currently doing for Bosley school but would not necessarily mean redeploying our staff. As all schools will be working closely together and monitoring all aspects of teching, finances, safeguarding then it would be far less likely that this would happen as this would have been picked up within the MAT and support would be put in at an early stage prior to Ofsted coming in.
|  |  |  | Would supply teachers be shared out between schools? | No, each school will choose and use their own supply teachers. There would obviosuly be opportuntity to share supply teachers if schools wanted to. |  | Who makes all the decisions regarding job conditions e.g pay increases, pensions etc | There has to be a central Pay Policy to ensure fairness and consistency across all the schools. Individual schools will continue to decide whether ateacher progresses on the pay-scale. Pensions are transferred across from the LA to the Mat on conversion. They will not be affected. |  |  |  |  | Will our Governing Board have an equal influence in the MAT? | As this is a new MAT and still formimg, there is currently space on the Board of Trustees for 2 members of Disley's Governing Board to sit. This means that they would have oversight of the operation and running of the MAT, Schools who join further down the line when the Board spaces have all been filled, would not have this option. This would be a benefit of joining the MAT at this stage.
If jobs become available within other MAT schools, would they be advertised within the MAT initially?
Note: The 'appropriately answered / resolved?' cells contain a colour-coded drop down list. At the end of the consultation process, we should expect to see a green 'yes' against every question within every SI

## Sheet5 (hidden)
Yes
No
Unanswered/unresolved

## Performance management
|  |  | 1 | 2 | 3 | 4 | 5
| Key outcomes |  | All children who attend Disley Primary School will have access to high quality teaching, resources and extended curriculum opportunities to allow them to achieve and attain well above National levels | Staff at Disley Primary School will be well supported, both within their own school and also within the MAT. This will include high quality professional development opportunities and peer-to-peer support. | Disley Primary School is able to sustain high quality staff and buildings financially in the long-term. | All children who live in Disley are able to attend Disley Primary School. | Disley Primary School is able to retain its' uniqeness as a school serving its' own community with the particular needs that brings.
| Measures of success |  | [To be completed. i.e. how are we going to measure whether we have been succesful and achieved this SI?] | [To be completed] | [To be completed] | [To be completed] | [To be completed]
| AAR | Autumn | [To be completed at least once every term. i.e. how are we progressing with this SI? What has been achieved? What is going well? Where are the remaining gaps? What are the remaining challenges?] | [To be completed] | [To be completed] | [To be completed] | [To be completed]
|  | Spring | [To be completed at least once every term. i.e. how are we progressing with this SI? What has been achieved? What is going well? Where are the remaining gaps? What are the remaining challenges?] | [To be completed] | [To be completed] | [To be completed] | [To be completed]
|  | Summer | [To be completed at least once every term. i.e. how are we progressing with this SI? What has been achieved? What is going well? Where are the remaining gaps? What are the remaining challenges?] | [To be completed] | [To be completed] | [To be completed] | [To be completed]
Note: This tab should be completed at the end of the consultation process if we decide to enter into the MAT. Tis will allow us to record our progress against each SI
AAR = after action review; SI = strategic imperative